## Doc Info
ProjectName
Estimation Sheet
Version 2
Document Information
Category
Document
Document Code
Version:
Status:
Author(s):
Reviewer(s):
Approver(s):
Effective Date:
Disclaimer:
Revision History
| Author(s) | Date | Version | Description of Change

## Checklist
Checklist
Sr. No. | Checkpoint | Yes/No | If No, mention reason
1 | Have you cross check Estimates formula?
2 | Have you mentioned Hosting details?
3 | Have you put project level assumptions?
4 | Have you put feature level assumptions?
5 | Have you listed un-estimated features with questions?
6 | Have you gone through all provided documents and emails?
7 | Have you had business understanding session with Sales executive?
8 | Have you removed not required line items from the estimation sheet?
9 | Have you mentioned technology stack?
10 | Have you included Design team estimates?
11 | Have you included Unit Testing Time in the Estimates
12 | Have you included Estimates from the Test Team

## ModulesFeature List
Key Modules/ Feature
Sr. No. | Name
1 | Upload Excel Sheet & check File formatting:
2 | Parse, Read, and Sort Excel Data:
3 | Identify and Map Dimensions to Higher Categories
4 | Generate and View Graphic Output
5
6
7
8

## Estimates
No. | Task | Description | Est. (man Hours) | Assumption | Target Milestone
1 | Requirement Gathering & Analysis |  | 0
1.1 | Functional Requirements Documentation | Deliverables: Groomed User Stories with Acceptance Criteria containing outcome of Analysis of project requirements. It may also include Wireframes, Process Diagrams, Flow-charts, Work-Flow Diagrams and / or any other relevant diagrams where appropriate | 0
1.2 | Application UI / UX Design | Click through UIs using Invision or any other similar tool (click through UIs if required). (Maximum of 3 iterations) | 0
1.3 | Non-functional requirements | Testing, technology, security, scalability, compatibility, deployment, coding standard, TDD / non-TDD, development methodology, training etc. | 0 | NOTE: Exactly specify browser with versions, OS versions and devices etc. that will be used for actual testing and get cleint's agreement
2 | Project Planning & Monitoring |  | 0.75
2.1 | Project Management Plan |  | 0
2.2 | Project Monitoring and Control | Periodic status reviews (weekly status report), daily scrums, sprint review and milestone review meetings, retrospective meetings, keeping project management plan updated | 0.75
4 | Software Architecture & Design |  | 0
4.1 | System Architecture Diagrams | Deployment architectural diagrams, Logical Architecture, Physical Architecture | 0
4.2 | Database design | ERD, Data Dictionary | 0
4.3 | Integration Design |  | 0
5 | Development Setup |  | 0.5
5.1 | Development Environment Setup |  | 0.5
6 | Use Cases Development
| User's Web App |  | 30.75
| Upload Excel Sheet | The user should be able to upload an Excel sheet (.xlsx, .csv) through the system's interface. | 2
| System Validates file Format | The system should be validating the file format and structure to ensure it contains the required columns before processing. | 0.25
| Invalid File Error | If the file is invalid, an appropriate error message should be displayed. | 0.25
| Parse and Read Excel Sheet Data | Once the file is uploaded, the system should read the data and extract all relevant fields, including P Score, Z Score, and associated dimensions. | 4
| Sort Data Based on P Score and Z Score | The extracted data should be sorted in descending order based on the P Score. If multiple entries have the same P Score, sorting should be done based on the Z Score in descending order. | 2
| Identify the Highest Dimension | The system should analyze the sorted data to determine the highest occurring dimension based on the Z Score. | 0.25
| Map Identified Dimension to a Higher-Level Category | The system should map the highest identified dimension to a broader category (e.g., Anger maps to Sadness). This mapping should be based on predefined relationships stored in a reference database or configuration file. | 4
| Generate Sample Graphic Output | Using the identified highest category, the system should dynamically generate a graphical representation similar to the provided sample graphic. The graphic should include puzzle-like segmentation, text labels, and a visual representation of the highest-scoring category. | 16
| Provide Downloadable Output | Once the graphic is generated, the user should be able to download the output as an image file (PNG, JPG) or PDF. | 2
8 | Software Testing, Fixing and Verification |  | 2
| Functional Testing |  | 2
9 | User Acceptance Testing |  | 4
| UAT |  | 4
10 | Application Rollout |  | 2
| Deployment on production |  | 2
|  | Total Project Man Hours | 40

## Technology Stack
Technology Stack
Sr. No. | Development | Technology | Version
1
2
3
4
5
6

## Platform
Platform
List of front-end running environments.
Mobile Devies
Sr. No. | Category | Scope
1 | Device Support | • Android Phones: xxxhdpi,xxhdpi,xhdpi, hdpi and mdpi density • Apple Phones: iPhone 8 and above
2 | OS Version Support | • Android 7.0 & above • iOS 12 & above
3 | Orientation Support | Portrait only
4
Web Application
Sr. No. | Category | Scope
1 | Platform Support | • Desktop • Mobile • Tablet
2 | Browser Support [Version] | • IE 10 and above • Chrome • Safari • Firefox • Opera
3
4

## Dependencies
Dependencies
Sr. No. | Technical Dependencies | Due Date | Status
1
2
3
4
5
6
7
8
Sr. No. | People Dependencies | Due Date | Status
1 | Requirements Review and Sign-off
2 | Milestone-1 Review and Sign-off
3 | Milestone-2 Review and Sign-off
4 | Milestone-n Review and Sign-off
5 | Align UAT resources
6

## Project Assumptions
Project Assumptions
Sr. No. | Assumptions
1 | We are assuming that the data extracted from the uploaded Excel sheet will not be stored in the backend; it will be session-based and only accessible for the duration of the user session.​
2 | It is assumed that the system will only support .xlsx and .csv file formats for uploading and any other formats will not be accepted by the system.​
3 | We are assuming that the uploaded Excel file must contain specific required columns (P Score, Z Score, and associated dimensions).​
4
5
6
7
8
9
10

## Milestone Plan Summary
Milestone | Deliverables | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Requirement Gathering & Analysis | Functional Requirements Documentation Application UI / UX Design Non-functional requirements Software Architecture & Design Development Setup
Milestone 1 | Marketing Website Local partnership User's Login & Authentication Service Tiers Admin Web Panel CMS
UAT & Deployment | UAT / UAT Support Devops & Deployments
Closure & Sign off | Client signoff on UAT